## Sheet1
ASP - Group Project
Date | time axis 2022-05-02 to 2022-09-05
Phase | 2022-05-02: PLANNING; 2022-05-09: REQUIREMENTS; 2022-05-16: REQUIREMENTS; 2022-05-23: Design; 2022-06-19: Proposal draft; 2022-06-24: Proposal Review; 2022-06-26: Midterm Group submission; 2022-06-27: Midterm Proposal Deadline; 2022-09-04: Project Group submission; 2022-09-05: Project Submission Deadline
Event | 2022-05-02: Teams alocated on Coursera; 2022-05-03: Group introductions and initial contact on Slack; 2022-05-07: First team meeting; 2022-05-09: All team members to review the following for presentation at the next team meeting. - 'Big picture' requirements of the projects (i.e. what does the project need to do? What features does the software need? Etc.) - Coding style (i.e. does it need to be OOP? What is the standard comment/code style?) - What the best method will be for designing the software (i.e. UML or Class diagrams etc) -; 2022-05-14: Team Meeting 2 - Requirements Determine collective project requirements; 2022-05-15: All team members to review the following for presentation at the next team meeting. User requirements - functional requirements - technical requirements The overall aim of the project The key project stakeholders Explore other programs that provide a similar service to the one proposed; 2022-05-22: Team Meeting 3 - Finalising Requirements Determine collective project requirements and ensure everyone is happy with the plan moving forward; 2022-05-23: All team members to review the following for presentation at the next team meeting. - viability of using the svelte framework for web design Connor, Kashka, David - Start to scope pseudocode for certain functions that may be required in the project Ben, Thavelarn - Start to design the wireframes for the individual functionality and design of the project.; 2022-05-29: Team Meeting 4 - scheduled for 1400 GMT - link to be provided on Slack Initial design updates
Notes | 2022-05-07: Decision was made to make a utlity web application which will take data uploaded by the user (via SQL or file upload) and perform data science manipulation to generate data driven grpahics Javascript, HMTL and CSS will be the backbone of the project; 2022-05-14: Connor unable to attend due to medical appointments, information will be submitted to the Slack channel prior to the meeting.; 2022-05-22: Positive meeting with the following being discussed - Connor will take the team leader position after unianomous approval from the group. - Github has been updated with a file directory for each phase of the project - Requirements have been finalised pending review when the midterm marking rubric is released. - p5.js and charts.js will form the backbone of the project - the team will look into the viability of the svelte framework for ease of producing the frontend. This will be reviewed at the next team meeting - the project now enters the design phase. Ben and Thavelarn will scope wireframes, Connor, David and Kashka will scope pseudocode for some of the functions contained in the project. - The team meetings will now be held on Sundays at 1400GMT as it is more convenient to the team. - files uploaded to GitHub will be markdown file format from now on to allow ease of use within GitHub. There was an issue with .doc files in GitHub and would force each team member to download the file to see the contents
Today | 2022-05-02: 2022-05-22