## Sheet1
ASP - Group Project
Date | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-30 | 2022-05-31 | 2022-06-01 | 2022-06-02 | 2022-06-03 | 2022-06-04 | 2022-06-05 | 2022-06-06 | 2022-06-07 | 2022-06-08 | 2022-06-09 | 2022-06-10 | 2022-06-11 | 2022-06-12 | 2022-06-13 | 2022-06-14 | 2022-06-15 | 2022-06-16 | 2022-06-17 | 2022-06-18 | 2022-06-19 | 2022-06-20 | 2022-06-21 | 2022-06-22 | 2022-06-23 | 2022-06-24 | 2022-06-25 | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04 | 2022-09-05
Phase | PLANNING | [6 empty] | REQUIREMENTS | [6 empty] | REQUIREMENTS | [6 empty] | Design | [26 empty] | Proposal draft |  |  |  |  | Proposal Review |  | Midterm Group submission | Midterm Proposal Deadline | Sprint 1 - Software Development | [5 empty] | Sprint 2 - Software Development | [6 empty] | Sprint 3 - Software Development | [6 empty] | Sprint 4 - Software Development | [6 empty] | Sprint 5 - Software Development | [6 empty] | Sprint 6 - Software Development | [5 empty] | Sprint 7 - Software Development | [6 empty] | Testing & Evaluation | [14 empty] | Final Analysis | [5 empty] | Project Group submission | Project Submission Deadline
Event | Teams alocated on Coursera | Group introductions and initial contact on Slack |  |  |  | First team meeting |  | All team members to review the following for presentation at the next team meeting. - 'Big picture' requirements of the projects (i.e. what does the project need to do? What features does the software need? Etc.) - Coding style (i.e. does it need to be OOP? What is the standard comment/code style?) - What the best method will be for designing the software (i.e. UML or Class diagrams etc) - |  |  |  |  | Team Meeting 2 - Requirements Determine collective project requirements | All team members to review the following for presentation at the next team meeting. User requirements - functional requirements - technical requirements The overall aim of the project The key project stakeholders Explore other programs that provide a similar service to the one proposed | [6 empty] | Team Meeting 3 - Finalising Requirements Determine collective project requirements and ensure everyone is happy with the plan moving forward | All team members to review the following for presentation at the next team meeting. - viability of using the svelte framework for web design Connor, Kashka, David - Start to scope pseudocode for certain functions that may be required in the project Ben, Thavelarn - Start to design the wireframes for the individual functionality and design of the project. | [5 empty] | Team Meeting 4 - Design Initial design updates | To review the following for presentation at the next team meeting Connor, Kashka, David - Start to design the wireframes for the individual functionality and design of the project. Ben, Thavelarn - Start to scope pseudocode for certain functions that may be required in the project **IF TIME PERMITS** All team members Update the Requirements->Final_Requirements files within the GitHub repo. | [5 empty] | Team Meeting 5 - Design Collating all the design updates | Connor - Create voting options for the final Designs All team members - Update the files within the Github repo under Requirements (Github/agile/Requirements/Final_Requirements) - Vote on final designs once uploaded to the Slack channel | [5 empty] | Team Meeting 6 - Finalising Design Collating the team's voted ideas for the final design - this will be from a vote (likely on Slack) | All team members - Update the files within the Github repo under Requirements (Github/agile/Requirements/Final_Requirements) | [5 empty] | Proposal Meeting Distributing the tasks required for the Proposal submission | All Team members - Create midterm submission from the information contained within the Github/Requirements/Final_Requirements folder -> All information required to successfully answer the questions should be contained within these folders. |  |  |  | All team members - Review midterm submissions |  |  |  | Ben & Thavelarn - Develop basic HTML skeleton for the navigation bar / other areas of the program David, Kashka, Connor - Develop code for a reactive navigation bar (to be implemented later) - Develop code to utilise the host OS to select and load a specific file |  |  |  |  | Team Meeting 7 - Development Update Update on the project build | Ben & Thavelarn - Develop the HTML skeleton further - Add basic CSS to the design David, Kashka, Connor - Develop code implemeting charts.js - Develop code to implement a menu button | [5 empty] | Team Meeting 8 - Development Update Update on the project build | Ben & Thavelarn - Continue to tweak the front end - Look into finding/creating the pre-built data for the system. - Investigate implementing Google Big Query in a future sprint David & Connor & Kashka - Continue integration of backend features on the system. The next focus will be chart.js implementation and error management of the data. - Look at implementing an export feature of charts.js once it has been successfully implemented on the system. | [5 empty] | Team Meeting 9 - Development Update Update on the project build | Ben & Thavelarn - Add all features to the front end so the backend can link them Kashka - Create parsing function. Connor - Create navigation bar David - Charts.js linking | [5 empty] | Team Meeting 10 - Development Update Update on the project build | TBC | [5 empty] | Team Meeting 11 - Development Update Update on the project build | TBC | [5 empty] | Team Meeting 14 - Development Update Update on the project build | TBC | [5 empty] | Team Meeting 15 - T&E meeting Update on the project build | THIS WEEK MAY BE CONTINGENCY DEVELOPMENT TIME AS SPRINT 8 IF REQUIRED | [5 empty] | Team Meeting 15 - T&E meeting Update on the project build | [6 empty] | Team Meeting 16 - Final T&E meeting Update on the project build | Prepare group submission
Notes | [5 empty] | Decision was made to make a utlity web application which will take data uploaded by the user (via SQL or file upload) and perform data science manipulation to generate data driven grpahics Javascript, HMTL and CSS will be the backbone of the project | [6 empty] | Connor unable to attend due to medical appointments, information will be submitted to the Slack channel prior to the meeting. | [7 empty] | Positive meeting with the following being discussed - Connor will take the team leader position after unianomous approval from the group. - Github has been updated with a file directory for each phase of the project - Requirements have been finalised pending review when the midterm marking rubric is released. - p5.js and charts.js will form the backbone of the project - the team will look into the viability of the svelte framework for ease of producing the frontend. This will be reviewed at the next team meeting - the project now enters the design phase. Ben and Thavelarn will scope wireframes, Connor, David and Kashka will scope pseudocode for some of the functions contained in the project. - The team meetings will now be held on Sundays at 1400GMT as it is more convenient to the team. - files uploaded to GitHub will be markdown file format from now on to allow ease of use within GitHub. There was an issue with .doc files in GitHub and would force each team member to download the file to see the contents | [6 empty] | - Team is progressing well with initial designs. - The team will now produce the the opposite of the design they produced last week (wireframes -> pseudocode // pseudocode -> wireframes) - Team decided to have the project hosted on a web server once compelete | [7 empty] | ** IF REQUIRED ** REQUIREMENTS CONTINGENCY PERIOD - Ensure Requirements are fit for purpose against Midterm Rubric DESIGN CONTINGENCY PERIOD - Ensure all pseudocode elements are fit for purpose - Ensure all wireframes are fit for purpose - Ensure initial prototypes are viable - Ensure all intended technology is viable | [10 empty] | Final Requirements updates/submissions/edits before the midterm |  | Requirements deadline |  |  |  |  | PROPOSAL CONTINGENCY PERIOD - Ensure Proposal meets the requirements of the Rubric - Peer review each individual submission - Ensure all submissions cover the correct material |  |  |  | Initial HMTL skeleton produced with sample code created for the backend | [5 empty] | Front end mostly complete Backend featrues added - button link to chart.js and File load complete | [12 empty] | Accelerated MVP intended timeline Unable to achieve this timeline, review next week | [6 empty] | Accelerated MVP intended timeline | ADDITIONAL FEATURES IF MVP TIMELINE IS EARLY | [5 empty] | Intended MVP deadline | DEVELOPMENT CONTINGENCY PERIOD IF TIME PERMITS … Add in more features to the software If MVP NOT CREATED Continue with MVP development as a contingency period | [6 empty] | DEVELOPMENT CONTINGENCY PERIOD IF TIME PERMITS … Add in more features to the software If MVP NOT CREATED Continue with MVP development as a contingency period | [6 empty] | OPTIONAL DEVELOPMENT CONTINGENCY PERIOD IF FURTHER DEVELOPEMT IS NEEDED | [5 empty] | DEVELOPMENT DEADLINE
Today | 2022-07-24