## Sheet1
ASP - Group Project
Date | time axis 2022-05-02 to 2022-09-05
Phase | 2022-05-02: PLANNING; 2022-05-09: REQUIREMENTS; 2022-05-16: REQUIREMENTS; 2022-05-23: Design; 2022-06-19: Proposal draft; 2022-06-24: Proposal Review; 2022-06-26: Midterm Group submission; 2022-06-27: Midterm Proposal Deadline; 2022-09-04: Project Group submission; 2022-09-05: Project Submission Deadline
Event | 2022-05-02: Teams alocated on Coursera; 2022-05-03: Group introductions and initial contact on Slack; 2022-05-07: First team meeting; 2022-05-09: All team members to review the following for presentation at the next team meeting. - 'Big picture' requirements of the projects (i.e. what does the project need to do? What features does the software need? Etc.) - Coding style (i.e. does it need to be OOP? What is the standard comment/code style?) - What the best method will be for designing the software (i.e. UML or Class diagrams etc) -; 2022-05-14: Team Meeting 2 - Requirements Determine collective project requirements
Notes | 2022-05-07: Decision was made to make a utlity web application which will take data uploaded by the user (via SQL or file upload) and perform data science manipulation to generate data driven grpahics Javascript, HMTL and CSS will be the backbone of the project; 2022-05-14: Connor unable to attend due to medical appointments, information will be submitted to the Slack channel prior to the meeting.
Today | 2022-05-02: 2022-05-12